## Sheet1
| TASK | STARTDATE | ENDDATE
35 | [MEETING] Design review and final commercial proposal | 2016-12-08 | 2016-12-09
34 | [PP] Final detailed cost estimation | 2016-12-04 | 2016-12-08 | 2016-10-16 | 2016-12-31
33 | [DD] Requirement traceability | 2016-12-02 | 2016-12-04
32 | [DD] Algorithm design | 2016-11-29 | 2016-12-02
31 | [DD] Subcomponent interfaces design | 2016-11-24 | 2016-11-29 |  |  | GRIGIO | STEPS
30 | [DD] Subcomponent design | 2016-11-23 | 2016-11-29 |  |  | BLU | MEETING
29 | [MEETING] Model and architecture validation, cost update | 2016-11-22 | 2016-11-23 |  |  | VERDE | NICOMON
28 | [PP] Refine cost estimation | 2016-11-20 | 2016-11-22 |  |  | ROSSO | FINIE
27 | [DD] Platform discussion | 2016-11-19 | 2016-11-20 |  |  | ARANCIONE | BOTH
26 | [DD] State charts | 2016-11-13 | 2016-11-19
25 | [DD] Model architecture draft | 2016-11-13 | 2016-11-19
24 | [DD] High level architecture proposal | 2016-11-10 | 2016-11-13
23 | DD | 2016-11-10 | 2016-12-04
22 | [RASD] Requirements final | 2016-11-08 | 2016-11-10
21 | [MEETING] Present requirements, mockups and cost estimation | 2016-11-07 | 2016-11-08
20 | [PP] Rough cost estimation for meeting | 2016-11-04 | 2016-11-07
19 | [RASD] UI mockups | 2016-11-03 | 2016-11-05
18 | [RASD] Functional requirements refinement and analysis | 2016-10-31 | 2016-11-05
17 | [RASD] Final use-cases | 2016-10-31 | 2016-11-01
16 | [RASD] Final scenarios | 2016-10-31 | 2016-11-01
15 | [RASD] Final assumptions | 2016-10-31 | 2016-11-01
14 | [RASD] Final goals | 2016-10-31 | 2016-11-01
13 | [MEETING] Requirement draft and functionalities final | 2016-10-30 | 2016-10-31
12 | [RASD] Functional requirements draft | 2016-10-26 | 2016-10-30
11 | [RASD] Use-cases refinement | 2016-10-25 | 2016-10-28
10 | [RASD] Scenario refinement | 2016-10-25 | 2016-10-28
9 | [RASD] Assumption refinement | 2016-10-24 | 2016-10-25
8 | [RASD] Goal refinement | 2016-10-24 | 2016-10-25
7 | [MEETING] General functionalities validation | 2016-10-23 | 2016-10-24
6 | [RASD] Scenarios draft | 2016-10-18 | 2016-10-23
5 | [RASD] Use-cases draft | 2016-10-18 | 2016-10-23
4 | [RASD] Assumptions first draft | 2016-10-17 | 2016-10-18
3 | [RASD] Draft of GOALS (main functionalities) | 2016-10-16 | 2016-10-20
2 | [MEETING] Project discussion, QA | 2016-10-16 | 2016-10-17
1 | RASD | 2016-10-16 | 2016-11-10
| TASK | STARTDATE | ENDDATE
21 | [MAINTENANCE] Bug fixing and updates | 2017-05-01 | 2018-01-01
20 | SYSTEM IS ONLINE | 2017-05-01 | 2018-01-01
19 | [DEP] Mobile deployment to public stores | 2017-04-30 | 2017-05-01
18 | [MEETING] Worker and admin teaching | 2017-04-27 | 2017-04-30
17 | [DEP] Mobile deployment to internals (worker, admin) | 2017-04-27 | 2017-04-28
16 | [DEP] System deployment | 2017-04-25 | 2017-04-27
15 | DEPLOYMENT | 2017-04-25 | 2017-05-01
14 | [DEV] Documentation review | 2017-04-23 | 2017-04-25
13 | [DEV] Refinements | 2017-04-19 | 2017-04-25
12 | [MEETING] First demo to PowerEni | 2017-04-18 | 2017-04-19
11 | [DEV] Graphical improvemenst | 2017-04-12 | 2017-04-18
10 | [DEV] Improvements and bug fixing | 2017-04-12 | 2017-04-18
9 | [DEV] Internal demo | 2017-04-10 | 2017-04-12
8 | [DEV] System testing | 2017-04-05 | 2017-04-10
7 | [DEV] Integration testing | 2017-03-20 | 2017-04-05
6 | [DEV] Component development | 2017-03-01 | 2017-03-30
5 | [DEV] Unit testing | 2017-01-20 | 2017-03-01
4 | [DEV] Unit test preparation (vehicle test devices) | 2017-01-15 | 2017-01-20
3 | [DEV] Code inspection | 2016-12-31 | 2017-02-01
2 | [DEV] Sucomponent development | 2016-12-09 | 2017-03-01
1 | DEVELOPMENT | 2016-12-09 | 2017-04-25